## Sheet1
Task | Developer | Completion Date
Create multi-dimensional database | Adam Shehadeh | 2018-09-26
Create new cloudsite to debug code against (with PHP and MySQL) | Adam Shehadeh | 2018-09-30
Create MySQL database structure for application consumption | Angel Todev | 2018-10-02
Complete PHP data layer of application to perform database interactions | Adam Shehadeh | 2018-11-04
Complete reporting page with sufficient formatting (HTML & CSS) | Angel Todev | 2018-11-06
Verify printability with multiple report forms | Adam Shehadeh | 2018-11-07
Complete login system | Adam Shehadeh | 2018-10-21
Reach out to business | Angel Todev | 2018-10-20
Schedule initial meeting with business | Angel Todev | 2018-10-23
Create staff information page with picture and other user information | Adam Shehadeh | In Progress
Verify that publishing methods of websites are acceptable | Angel Todev | 2018-10-26
Complete Ownership transfer after project completion | Angel Todev | 2018-11-12
Demo Prototype to business | Adam Shehadeh | In Progress
Complete evaluation usability testing | Angel Todev | In Progress
Complete evaluation functional testing | Adam Shehadeh | In Progress
Complete evaluation database testing | Adam Shehadeh | In Progress
Complete evaluation security testing | Angel Todev | In Progress
Dashboard – Fix recent surveys window rendering. Ask Ryan what we should do to this page? | Adam Shehadeh | Waiting on
Surveys – (write to database) Mostly done, get confirmation | Adam Shehadeh | Waiting on
Charts – Change to employee report? Render screen correctly. | Angel Todev | Waiting on
New User – Ask about fields above | Angel Todev | Waiting on
Remove User – Follows new user | Angel Todev | Waiting on
Profile – What do we need to display on this? Allow editing? | Adam Shehadeh | Waiting on
Accounts – Settings & Help, what should these do? | Adam Shehadeh | Waiting on

## Sheet2
What additional user information do we want to store?
-id
-username
-passwd
-role
-self_survey_id
-admin_survey_id
Plans per page:
Dashboard – Fix recent surveys window rendering. Ask Ryan what we should do to this page?
Surveys – (write to database) Mostly done, get confirmation
Charts – Change to employee report? Render screen correctly.
New User – Ask about fields above
Remove User – Follows new user
Profile – What do we need to display on this? Allow editing?
Accounts – Settings & Help, what should these do?