## Project Plan
Project Plan | Project Start Date | Project End Date
| 2018-01-22 | 2018-04-28
Survey
Name | Phase | How long will this take - Start | How long will this take - End | Duration
Customer Meeting | Done | 2018-01-22 | 2018-02-06 | 16
Requirements | Done | 2018-02-05 | 2018-02-09 | 5
CSS/HTML Format (Main Page Survey) | Done | 2018-02-15 | 2018-02-18 | 4
Mind Map | Done | 2018-02-15 | 2018-02-18 | 4
Database Design Survey | Working on it | 2018-02-20 | 2018-02-23 | 4
Integrate Database onto Surveys | Working on it | 2018-02-21 | 2018-03-05 | 13
Code on Pretest Page Adding buttons | Working on it | 2018-02-21 | 2018-03-05 | 13
Code on Post Test Page Adding buttons |  | 2018-03-05 | 2018-03-12 | 8
Report CSV Files (Individual) |  | 2018-03-10 | 2018-03-11 | 2
Report CSV Files (Composite) |  | 2018-03-10 | 2018-03-11 | 2
Test Survey
Name | Phase | How long will this take - Start | How long will this take - End | Duration
Userabilty |  | 2018-03-10 | 2018-03-13 | 4
Functionality |  | 2018-03-05 | 2018-03-12 | 8
Database Testing
Security Testing
Evaluation
Name | Phase | How long will this take - Start | How long will this take - End | Duration
Evaluation page HTML and CSS style | Working on it | 2018-02-21 | 2018-03-08 | 16
Design User Interface | Working on it | 2018-02-21 | 2018-03-06 | 14
Database Design for Evaluation |  | 2018-03-05 | 2018-03-13 | 9
Database Securities for Evaluation |  | 2018-03-06 | 2018-03-12 | 7
Database Evaluation Integrated with Evaluation Survey |  | 2018-03-10 | 2018-03-11 | 2
Reports
Graph
Evaluation Test
Name | Phase | How long will this take - Start | How long will this take - End | Duration
Userabilty
Functionality
Database Testing
Security Testing

## Survey Test
Survey Testing
Usability
Name | Status
Web Page content is spell correcty
Buttons are in standard format and size
Images are there
Click on Pre Test
Navigate through questions
Check if questions are split onto multiple pages.
Functional
Name | Status
Type on name field and do NOT fill up all the field then click on either button
Check error message until requirements of field are filled.
Type name and ensures all field are fill.
Click on Pre Test
Answer questions by clicking on the bubbles
Click submit when not all questions are not fill out
Check in questions are highlighted that are not answer
Display error message of not answering all the questions
Click submit when all the question are fill out
Do the same thing for Post from # 1- 9
Database Testing
Name | Status
Verify database name with page
Verify Primary and foreign key on each table
Add SQL statements to test store procedures
Verify data is probably saved onto database
Verify the encrypted data in the database
Verify data displayed on the front end is the same as the back end
Verify data validity by inserting invalid data in the database.
Security Test
Name | Status
Verify surveys are saved through user name.
Verify a two way authentications.

## Evaultion Test
Evaluation Test
Usability
Name | Status
Web Page content is spell correcty
Buttons are in standard format and size
Images are there
Login on to page with correct login page and password
Navigate through login pages
Buttons and options are displayed correctly
Reports or graph display correctly
Functional
Name | Status
Type on name field and do NOT fill up all the field then click on either button
Check error message until requirements of field are filled.
Type name and ensures all field are fill.
Login
Click on buttons or links
Database Testing
Name | Status
Verify database name with page
Verify Primary and foreign key on each table
Add SQL statements to test store procedures
Verify data is probably saved onto database
Verify the encrypted data in the database
Verify data displayed on the front end is the same as the back end
Verify data validity by inserting invalid data in the database.
Security Test
Name | Status
Verify password is encrypted
Verify passwords rules are implemented to login page.
Verify to access the secured and non secured web pages directly without login.
Verify SQL injection attacks
Verify users cannot access admin page (user roles and their rights)