## Sheet1
Task | Developer | Completion Date | Done
Create multi-dimensional database | Adam Shehadeh | 2018-09-26 | X
Create new cloudsite to debug code against (with PHP and MySQL) | Adam Shehadeh | 2018-09-30 | X
Create MySQL database structure for application consumption | Angel Todev | 2018-10-02 | X
Complete PHP data layer of application to perform database interactions | Adam Shehadeh
Complete reporting page with sufficient formatting (HTML & CSS) | Angel Todev
Verify printability with multiple report forms | Adam Shehadeh
Complete login system | Adam Shehadeh | 2018-10-21 | x
Reach out to business | Angel Todev | 2018-10-20 | x
Schedule initial meeting with business | Angel Todev | 2018-10-23 | x
Create staff information page with picture and other user information | Adam Shehadeh
Verify that publishing methods of websites are acceptable | Angel Todev | 2018-10-26 | x
Complete Ownership transfer after project completion | Angel Todev
Demo Prototype to business | Adam Shehadeh
Complete evaluation usability testing | Angel Todev
Complete evaluation functional testing | Adam Shehadeh
Complete evaluation database testing | Adam Shehadeh
Complete evaluation security testing | Angel Todev
Dashboard – Fix recent surveys window rendering. Ask Ryan what we should do to this page? | Adam Shehadeh
Surveys – (write to database) Mostly done, get confirmation | Adam Shehadeh
Charts – Change to employee report? Render screen correctly. | Angel Todev
New User – Ask about fields above | Angel Todev
Remove User – Follows new user | Angel Todev
Profile – What do we need to display on this? Allow editing? | Adam Shehadeh
Accounts – Settings & Help, what should these do? | Adam Shehadeh

## Sheet2
What additional user information do we want to store?
-id
-username
-passwd
-role
-self_survey_id
-admin_survey_id
Plans per page:
Dashboard – Fix recent surveys window rendering. Ask Ryan what we should do to this page?
Surveys – (write to database) Mostly done, get confirmation
Charts – Change to employee report? Render screen correctly.
New User – Ask about fields above
Remove User – Follows new user
Profile – What do we need to display on this? Allow editing?
Accounts – Settings & Help, what should these do?